## 01 ¦ Gantt Chart & Burndown
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Proposal |  | 2.5 | 2.5 | 0 |  |  |  |  | 100%
1.1 | Identify Target User and Project Scope | David, ER | 0.5 | 0.5 | 0 |  | 2026-05-20 | 2026-05-20 | 1 | 100% | bar: WEEK 1 W
1.2 | Define problem statement and objectives |  | 0.5 | 0.5 | 0 |  | 2026-05-20 | 2026-05-20 | 1 | 100% | bar: WEEK 1 W
1.3 | Determine system requirements and features | Pagala, DK | 0.5 | 0.5 | 0 |  | 2026-05-20 | 2026-05-21 | 2 | 100% | bar: WEEK 1 R
1.4 | Identify functional and non-functional requirements | Valencia, JJ | 1 | 1 | 0 |  | 2026-05-20 | 2026-05-21 | 2 | 100% | bar: WEEK 1 R
2 | System Design |  | 3 | 3 | 0 |  |  |  |  | 100%
2.1 | Design Use Case Diagram (UMLet) | Pagala, DK | 1.5 | 1.5 | 0 |  | 2026-05-20 | 2026-05-21 | 2 | 100% | bar: WEEK 1 R to WEEK 2 F
2.2 | Design Class Diagram (UMLet) |  | 1.5 | 1.5 | 0 |  | 2026-05-20 | 2026-05-21 | 2 | 100% | bar: WEEK 1 R to WEEK 2 F
2.3 | Develop 3-Tier Architecture Diagram | David, ER | 1.5 |  |  |  | 2026-05-21 | 2026-05-22 | bar: WEEK 1 F to WEEK 2 F
3 | Data Collection |  | 1.5 | 0 | 1.5 |  |  |  |  | 0%
3.1 | Download and organize plant disease datasets | Valencia, JJ | 0.5 |  | 0.5 |  |  |  | 1 | 0%
3.2 | Image preprocessing and augmentation |  | 1 |  | 1 |  |  |  | 1 | 0%
4 | Backend Development and Model Training |  | 12 | 0 | 8 |  |  |  |  | 0%
4.1 | CNN Development | Valencia, JJ | 4 |  | 4 |  |  |  | 1 | 0% | bar: WEEK 2 M to WEEK 3 M
4.1.1 | Design CNN architecture and parameters |  | 2 | bar: WEEK 2 M to WEEK 3 M
4.1.2 | Implement model using TensorFlow | Pagala, DK | 2 | bar: WEEK 2 M to WEEK 3 T
4.2 | Train CNN model using prepared dataset |  | 4 |  | 4 |  |  |  | 1 | 0% | bar: WEEK 3 T to WEEK 3 R
4.3 | Evaluate accuracy and validation performance |  | 3 | bar: WEEK 3 R to WEEK 3 F
5 | Frontend Development |  | 34.5 | 0 | 0 |  |  |  |  | 0%
5.1 | Design UI mockup | David, ER | 5 | bar: WEEK 4 M to WEEK 4 W
5.2 | Connect UI with CNN prediction model |  | 2 | bar: WEEK 4 W to WEEK 4 R
6 | Testing & Debugging |  | 21.5 | 0 | 0 |  |  |  |  | 0%
6.1 | Perform functionality testing | David, ER | 3 | bar: WEEK 4 R to WEEK 5 F
6.2 | Analyze model performance metrics |  | 3 | bar: WEEK 4 R to WEEK 5 F
7 | Documentation |  | 10.5 | 0 | 0 |  |  |  |  | 0%
7.1 | Complete Project Proposal | All | 5
7.2 | Write Final Project Documentation |  | 5
7.3 | Create GitHub Repository | Pagala, DK | 0.5
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/ DAYS
| BURNDOWN DATA | TOTAL HOURS | 47 | 5.5 | 9.5 | 50 | 0.94 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 47 | 46.06 | 45.12 | 44.18 | 43.24 | 42.3 | 41.36 | 40.42 | 39.48 | 38.54 | 37.6 | 36.66 | 35.72 | 34.78 | 33.84 | 32.9 | 31.96 | 31.02 | 30.08 | 29.14 | 28.2 | 27.26 | 26.32 | 25.38 | 24.44 | 23.5 | 22.56 | 21.62 | 20.68 | 19.74 | 18.8 | 17.86 | 16.92 | 15.98 | 15.04 | 14.1 | 13.16 | 12.22 | 11.28 | 10.34 | 9.4 | 8.46 | 7.52 | 6.58 | 5.64 | 4.7 | 3.76 | 2.82 | 1.88 | 0.94 | 0 | -0.94 | -1.88 | -2.82 | -3.76 | -4.7 | -5.64 | -6.58 | -7.52 | -8.46 | HOURS
[10 empty] | ESTIMATE | 47 | 39 | 19 | -11 | -51 | -71 | -82 | -98 | -140 | -185 | -205 | -215 | -231 | -255 | -303 | -323 | -327 | -332 | -336 | -344 | -352 | -357 | -362 | -367 | -370 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -18232
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 39 | 19 | -11 | -51 | -71 | -82 | -98 | -140 | -185 | -205 | -215 | -231 | -255 | -303 | -323 | -327 | -332 | -336 | -344 | -352 | -357 | -362 | -367 | -370 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -372 | -18651
BURNDOWN CHART
CLICK HERE TO CREATE IN SMARTSHEET

## Release Backlog
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
[6 empty] | 1 | Complete |  | Complete | 1
[6 empty] | 2 | Complete |  | Overdue | 2
[6 empty] | 8 | Complete |  | In Progress | 4
[6 empty] | 8 | Overdue |  | Not Started | 8
[6 empty] | 4 | In Progress |  |  | 16
[6 empty] | 80 | In Progress |  |  | 24
[6 empty] | 16 | Not Started |  |  | 40
[6 empty] | 8 | Not Started |  |  | 80
4
2
24
40

## User Stories or Tasks
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED