## Agile Sprint Burndown
PROJECT SCHEDULE (Gantt Chart)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Proposal Completion | 2
Write Group’s Analysis section |  | Lam, RJ | Complete | 2
Create Draft for Project Proposal |  |  | Complete | 3 | 3 | 0 | 0 | 0 | 0 | 0
Design cover page, formatting, Build Gantt Chart table (Excel/Sheets) |  | Pagala, DK | Complete | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Create Use Case Diagram (UMLet) |  | Esperanza, JA | In Progress | 2 | 1 | 1 | 0 | 0 | 0 | 0
Create Class Diagram (UMLet) |  | Pagala, DK | Complete | 2 | 2 | 0 | 0 | 0 | 0 | 0
System Design Phase | 5
Design MVC Architecture |  | Lam, RJ | Not Started
Design Database Schema (ER Diagram + Tables) |  | Esperanza, JA | Not Started
Plan API Endpoints (FastAPI Routes) |  | Pagala, DK | Not Started
UI Wireframe Design (Flet) |  |  | Not Started
Backend Development (FastAPI)
Implement FastAPI Server |  | Lam, RJ | Not Started
Implement Scheduling Algorithm (Dijkstra / A*) |  |  | Not Started
Develop RideRequest, Driver, and User Modules |  | Esperanza, JA | Not Started
Integrate Google Maps API for Routing |  |  | Not Started
Frontend Development (Flet)
Build User Booking Interface |  | Pagala, DK | Not Started
Build Driver Dashboard |  |  | Not Started
Connect UI to FastAPI endpoints |  | Lam, RJ | Not Started
Database Setup & Integration
Setup MongoDB / SQL database |  | Esperanza, JA | Not Started
Implement CRUD operations via ORM |  |  | Not Started
Testing & Debugging
Unit Testing (Backend + API) |  | Lam, RJ | Not Started
UI Testing (Accessibility checks) |  | Pagala, DK | Not Started
Integration Testing |  | Esperanza, JA | Not Started
Analytics & Visualization (Matplotlib)
Generate ride frequency and wait time graphs |  | Esperanza, JA | Not Started
Create service coverage visualization |  | Pagala, DK | Not Started
Documentation
Write final documentation (Report + Screenshots) |  | All | Not Started
TOTAL |  |  |  | 9.5 | 6.5 | 1 | 0 | 0 | 0 | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.