## Gantt Chart & Burndown
Development of a Raspberry Pi-Powered OCR Text Detection and English-Tagalog Translation System
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | PROJECT INITIATION |  | 5 | 5 | 0 |  |  |  |  | 100%
1.1 | Finalize Project Scope and Objectives | Denise Pagala | 0.5 | 0.5 | 0 |  |  |  | 1 | 100%
1.2 | Finalize Project Scope and System Requirements | Cristel Estilo | 1 | 1 | 0 |  |  |  | 1 | 100%
1.3 | Finalize Project Documentation | Cristel Estilo | 0.5 | 0.5 | 0 |  |  |  |  | 100%
1.3 | Create Required Diagrams (Case Diagrams, Hardware, Software) | Justin Ngo | 3 | 3 | 0 |  |  |  | 1 | 100%
2 | SYSTEM SETUP |  | 0 | 0 | 0
2.1 | Set Up Raspberry Pi 4B and USB Webcam |  |  |  | 0 |  |  |  | 1
2.2 | Develop Image Capture and OCR Module |  |  |  | 0 |  |  |  | 1
2.3 | Develop English-to-Tagalog Processing Module |  |  |  | 0 |  |  |  | 1
2.4 | Set Up FastAPI Client–Server Communication |  |  |  | 0 |  |  |  | 1
2.5 | Develop and Integrate Graphical User Interface |  |  |  | 0 |  |  |  | 1
3 | SYSTEM DEVELOPMENT |  | 0 | 0 | 0
3.1 | Integrate OCR, Backend, and Translation Modules |  |  |  | 0 |  |  |  | 1
3.2 | Perform End-to-End System Testing |  |  |  | 0 |  |  |  | 1
3.3 | Resolve Accuracy, Latency, and Integration Issues |  |  |  | 0 |  |  |  | 1
4 | PROJECT DOCUMENTATION AND SOURCE CODE |  | 0 | 0 | 0
4.1 | Complete and Revise Project Documentation |  |  |  | 0 |  |  |  | 1
4.2 | Organize and Clean Source Code |  |  |  | 0 |  |  |  | 1
4.3 | Prepare Dataset and Required Project Files |  |  |  | 0 |  |  |  | 1
4.4 | Create GitHub Repository and README.md |  |  |  | 0 |  |  |  | 1
5 | PROJECT PRESENTATION |  | 0 | 0 | 0
4.1 | Prepare Presentation Content and Demonstration |  |  |  | 0 |  |  |  | 1
4.2 | Record Live System Demonstration |  |  |  | 0 |  |  |  | 1
4.3 | Record and Edit 10–15 Minute Presentation Video |  |  |  | 0 |  |  |  | 1
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/ DAYS
| BURNDOWN DATA | TOTAL HOURS | 5 | 5 | 0 | 60 | 0.083333 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 5 | 4.9167 | 4.8333 | 4.75 | 4.6667 | 4.5833 | 4.5 | 4.4167 | 4.3333 | 4.25 | 4.1667 | 4.0833 | 4 | 3.9167 | 3.8333 | 3.75 | 3.6667 | 3.5833 | 3.5 | 3.4167 | 3.3333 | 3.25 | 3.1667 | 3.0833 | 3 | 2.9167 | 2.8333 | 2.75 | 2.6667 | 2.5833 | 2.5 | 2.4167 | 2.3333 | 2.25 | 2.1667 | 2.0833 | 2 | 1.9167 | 1.8333 | 1.75 | 1.6667 | 1.5833 | 1.5 | 1.4167 | 1.3333 | 1.25 | 1.1667 | 1.0833 | 1 | 0.91667 | 0.83333 | 0.75 | 0.66667 | 0.58333 | 0.5 | 0.41667 | 0.33333 | 0.25 | 0.16667 | 0.083333 | HOURS
[10 empty] | ESTIMATE | 5 | -3 | -23 | -53 | -93 | -113 | -124 | -140 | -182 | -227 | -247 | -257 | -273 | -297 | -345 | -365 | -369 | -374 | -378 | -386 | -394 | -399 | -404 | -409 | -412 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -20752
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | -3 | -23 | -53 | -93 | -113 | -124 | -140 | -182 | -227 | -247 | -257 | -273 | -297 | -345 | -365 | -369 | -374 | -378 | -386 | -394 | -399 | -404 | -409 | -412 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -414 | -21171
BURNDOWN CHART
CLICK HERE TO CREATE IN SMARTSHEET