## Gantt Chart & Burndown
Development of a Raspberry Pi-Powered OCR Text Detection and English-Tagalog Translation System
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | PROJECT INITIATION |  | 5 | 5 | 0 |  |  |  |  | 100%
1.1 | Finalize Project Scope and Objectives | Denise Pagala | 0.5 | 0.5 | 0 | 1 |  |  | 1 | 100% | bar: WEEK 1 T
1.2 | Finalize Project Scope and System Requirements | Cristel Estilo | 1 | 1 | 0 | 1 |  |  | 1 | 100% | bar: WEEK 1 R
1.3 | Finalize Project Documentation | Cristel Estilo | 0.5 | 0.5 | 0 | 1 |  |  |  | 100% | bar: WEEK 1 R to WEEK 2 F
1.3 | Create Required Diagrams (Case Diagrams, Hardware, Software) | Justin Ngo | 3 | 3 | 0 | 1 |  |  | 1 | 100% | bar: WEEK 1 R to WEEK 2 F
2 | SYSTEM SETUP AND INITIAL DEVELOPMENT |  | 2.5 | 2.5 | 0 |  |  |  |  | 100%
2.1 | Set Up Python Development Environment | Denise Pagala | 0.5 | 0.5 | 0 | 1 |  |  |  | 100%
2.2 | Develop Initial English-to-Tagalog Translation Module | Denise Pagala | 3 | 3 | 0 | 1 |  |  |  | 100%
2.3 | Test and Evaluate Translation Model | Justin Ngo | 1.5 | 1.5 | 0 | 1 |  |  |  | 100%
2.4 | Set Up and Prepare OCR Dataset | Cristel Estilo | 1.5 | 1.5 | 0 | 2 |  |  |  | 100%
2.5 | Develop and Test OCR Module using Tesseract | Denise Pagala | 1 | 1 | 0 | 2 |  |  | 1 | 100%
2.6 | Perform OCR Preprocessing and Accuracy Testing | Justin Ngo | 1.5 | 1.5 | 0 | 2 |  |  | 1 | 100%
3 | SYSTEM DEVELOPMENT AND INTEGRATION |  | 3.5 | 3.5 | 0 |  |  |  |  | 100%
3.1 | Integrate OCR and English-to-Tagalog Translation | Denise Pagala | 1.5 | 1.5 | 0 | 3 |  |  | 1 | 100% | bar: WEEK 3 T
3.2 | Set Up FastAPI Client–Server Communication | Cristel Estilo | 2 | 2 | 0 | 3 |  |  | 1 | 100% | bar: WEEK 3 T
3.3 | Develop Graphical User Interface using Flet | Cristel Estilo | 1.5 | 1.5 | 0 | 3 |  |  |  | 100% | bar: WEEK 3 T to WEEK 3 W
3.4 | Integrate OCR, Backend, Translation, and GUI | Denise Pagala | 2 | 2 | 0 | 3 |  |  |  | 100% | bar: WEEK 3 R to WEEK 3 F
3.5 | Develop Image Capture Module using USB Webcam | Denise Pagala | 1 | 1 | 0 | 3 |  |  |  | 100% | bar: WEEK 4 M
3.6 | Integrate System with Raspberry Pi 4B | Denise Pagala | 2.5 | 2.5 | 0 | 3 |  |  |  | 100% | bar: WEEK 4 M to WEEK 4 T
4 | SYSTEM TESTING AND IMPROVEMENT |  | 6.5 | 6.5 | 0 |  |  |  |  | 100%
4.1 | Perform End-to-End System Testing | Justin Ngo | 2 | 2 | 0 | 3 |  |  | 1 | 100% | bar: WEEK 4 W
4.2 | Evaluate OCR and Translation Accuracy | Justin Ngo | 1.5 | 1.5 | 0 | 3 |  |  | 1 | 100% | bar: WEEK 4 W
4.3 | Evaluate System Response Time and Performance | Cristel Estilo | 1.5 | 1.5 | 0 | 3 |  |  | 1 | 100% | bar: WEEK 4 R
4.4 | Resolve Accuracy, Latency, and Integration Issues | Denise Pagala | 1.5 | 1.5 | 0 | 3 |  |  | 1 | 100% | bar: WEEK 4 R
4.5 | Perform Final System Validation | Justin Ngo | 1.5 | 1.5 | 0 | 3 |  |  |  | 100% | bar: WEEK 4 F to WEEK 5 F
5 | PROJECT DOCUMENTATION AND SOURCE CODE |  | 3.5 | 3.5 | 0 |  |  |  |  | 100%
5.1 | Complete and Revise Project Documentation | Everyone | 2 | 2 | 0 | 3 |  |  | 1 | 100%
5.2 | Organize and Clean Source Code | Denise Pagala | 0.5 | 0.5 | 0 | 3 |  |  | 1 | 100%
5.3 | Finalize Dataset and Required Project Files | Cristel Estilo | 1 | 1 | 0 | 1 |  |  | 1 | 100%
5.4 | Create and Update GitHub Repository and README.md | Denise Pagala | 0.5 | 0.5 |  | 1 |  |  |  | 100%
6 | PROJECT PRESENTATION |  | 3 | 3 | 0 |  |  |  |  | 100%
6.1 | Prepare Presentation Content and Demonstration | Cristel Estilo | 2 | 2 | 0 | 3 |  |  | 1 | 100%
6.2 | Record Live System Demonstration | Denise Pagala | 0.5 | 0.5 | 0 | 3 |  |  | 1 | 100%
6.3 | Record and Edit 10–15 Minute Presentation Video | Everyone | 0.5 | 0.5 | 0 | 3 |  |  | 1 | 100%
6.4 | Finalize Presentation and Project Submission | Cristel Estilo | 1 | 1 | 0 | 3 |  |  | 1 | 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/ DAYS
| BURNDOWN DATA | TOTAL HOURS | 17.5 | 17.5 | 0 | 60 | 0.29167 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 17.5 | 17.2083 | 16.9167 | 16.625 | 16.3333 | 16.0417 | 15.75 | 15.4583 | 15.1667 | 14.875 | 14.5833 | 14.2917 | 14 | 13.7083 | 13.4167 | 13.125 | 12.8333 | 12.5417 | 12.25 | 11.9583 | 11.6667 | 11.375 | 11.0833 | 10.7917 | 10.5 | 10.2083 | 9.9167 | 9.625 | 9.3333 | 9.0417 | 8.75 | 8.4583 | 8.1667 | 7.875 | 7.5833 | 7.2917 | 7 | 6.7083 | 6.4167 | 6.125 | 5.8333 | 5.5417 | 5.25 | 4.9583 | 4.6667 | 4.375 | 4.0833 | 3.7917 | 3.5 | 3.2083 | 2.9167 | 2.625 | 2.3333 | 2.0417 | 1.75 | 1.4583 | 1.1667 | 0.875 | 0.58333 | 0.29167 | HOURS
[10 empty] | ESTIMATE | 17.5 | 9.5 | -10.5 | -40.5 | -80.5 | -100.5 | -111.5 | -127.5 | -169.5 | -214.5 | -234.5 | -244.5 | -260.5 | -284.5 | -332.5 | -352.5 | -356.5 | -361.5 | -365.5 | -373.5 | -381.5 | -386.5 | -391.5 | -396.5 | -399.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -20002
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 9.5 | -10.5 | -40.5 | -80.5 | -100.5 | -111.5 | -127.5 | -169.5 | -214.5 | -234.5 | -244.5 | -260.5 | -284.5 | -332.5 | -352.5 | -356.5 | -361.5 | -365.5 | -373.5 | -381.5 | -386.5 | -391.5 | -396.5 | -399.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -401.5 | -20421
BURNDOWN CHART
CLICK HERE TO CREATE IN SMARTSHEET